AGRI-SAGE

TEAM SPRINT PLAN & GITHUB GUIDE

5 Beginners · Free Tools · GitHub Architecture · October 1st Demo · Step-by-Step for Every Member

| Field | Detail |
| --- | --- |
| Team | 5 members — all beginners — parallel work — one project |
| HR Demo Deadline | October 1st — 50% implementation required with working demo |
| Today's Date | September 9, 2026 |
| Days Until Demo | 22 days |
| Build Tools | VSCode Copilot (free) · Cline + Gemini API (free) · GitHub Copilot free tier |
| Zero Cost | All tools, AI, infrastructure, hosting — free of cost |

# SECTION 1: OCTOBER 1st DEMO — THE PLAN

🎯 22 DAYS TO DEMO. 50% implementation required. This section defines exactly what must be working by October 1st.

## 1.1 What '50% Implementation' Means for This Project

The HR demo must show a WORKING app — not slides, not mockups. A real Android app on a real phone doing real things. Here is exactly what must work by October 1st:

| Feature | Demo Ready? | Who Builds It | Status |
| --- | --- | --- | --- |
| Android app installs and opens on phone | MUST HAVE | Member 3 | Not started |
| Farmer registers with phone OTP | MUST HAVE | Member 1 | Not started |
| Farm and crop setup wizard | MUST HAVE | Member 3 | Not started |
| Take crop photo with quality indicator | MUST HAVE | Member 3 | Not started |
| Disease detection from photo (offline ONNX) | MUST HAVE | Member 4 | Not started |
| Advisory result screen with evidence | MUST HAVE | Member 2+3 | Not started |
| Weather integration and indicators | MUST HAVE | Member 2 | Not started |
| Home screen with morning briefing card | MUST HAVE | Member 3 | Not started |
| Malayalam language throughout | MUST HAVE | Member 3 | Not started |
| Offline mode — app works without internet | MUST HAVE | Member 3+4 | Not started |
| Backend API running on server | MUST HAVE | Member 1 | Not started |
| Government scheme matching (basic) | NICE TO HAVE | Member 2 | Secondary |
| Voice input/output | NICE TO HAVE | Member 3 | Secondary |
| Simulation scenarios | NOT NEEDED for demo | Member 2 | Phase 3 |
| Market prices | NOT NEEDED for demo | Member 4 | Phase 4 |

⚠ Focus ALL energy on MUST HAVE items first. Do not start NICE TO HAVE until all MUST HAVE items work. The HR expects to see a farmer take a photo and get an advisory in Malayalam — that is the core demo.

## 1.2 The 22-Day Sprint Schedule

| Days | Dates | Focus | Goal by End of Period |
| --- | --- | --- | --- |
| Days 1-3 | Sep 10-12 | Setup: GitHub, tools, environment, all members onboarded | Every member has VSCode + Cline + Gemini API working. Repo created. Everyone has cloned it. |
| Days 4-7 | Sep 13-16 | Foundation: Backend running, Android project created, data files done | Backend /health endpoint returns 200. Android app opens on emulator. All JSON data files created. |
| Days 8-11 | Sep 17-20 | Core Build: Auth, farm CRUD, camera, vision model ONNX | Farmer can register, create farm, take photo. Vision ONNX runs on Android device. |
| Days 12-15 | Sep 21-24 | Intelligence: 6 agents, full advisory pipeline, advisory screen | POST /diagnose returns full advisory. Advisory screen shows on Android with confidence badge. |
| Days 16-18 | Sep 25-27 | Polish: Malayalam, home screen, offline mode, error handling | App works fully in Malayalam. Works offline. All error states handled gracefully. |
| Days 19-20 | Sep 28-29 | Integration: Connect Android to backend, end-to-end test | Full flow: photo → backend → advisory → screen. Works on real Android phone. |
| Days 21-22 | Sep 30 - Oct 1 | Demo prep: Fix bugs, prepare demo script, practice | App working smoothly. Demo script practiced. Every member knows their part of demo. |

## 1.3 Demo Script — What to Show HR

Practice this exact sequence 3 times before October 1st:

- 1. Open Agri-SAGE on Android phone. Show home screen in Malayalam. (30 seconds)

- 2. Explain: 'This is the farmer's daily view — morning briefing, quick actions, offline indicator.' (30 seconds)

- 3. Tap 'Check Crop'. Camera opens. Show quality indicator turning green. (30 seconds)

- 4. Take photo of a leaf (real plant). Show advisory loading screen with progress steps. (30 seconds)

- 5. Show advisory result: confidence badge, evidence section, recommended action, modelled estimate label. (60 seconds)

- 6. Tap voice button — advisory reads aloud in Malayalam. (20 seconds)

- 7. Show offline mode: turn on airplane mode, take another photo — advisory still works. (30 seconds)

- 8. Show government scheme card: 'PMFBY scheme available for this farmer.' (20 seconds)

- 9. Close with: 'This is Agri-SAGE — agricultural decision intelligence for Kerala farmers, built entirely free, offline-capable, in their language.' (30 seconds)

Total demo time: approximately 5 minutes. Practice until it is smooth with no hesitation.

# SECTION 2: GITHUB REPOSITORY SETUP

## 2.1 One-Time Setup — Member 1 Does This on Day 1

Member 1 (Team Lead) sets up the GitHub repository. All others clone it.

# MEMBER 1 ONLY — Do this first before anything else

# Step 1: Create repository on GitHub

# Go to github.com → Sign in → Click '+' top right → New repository

# Repository name: agrisage

# Description: Scalable Agricultural Guidance Engine - AI-powered farm advisory platform

# Visibility: Private (keep code private)

# Initialize: Add README ✓ | Add .gitignore: Python ✓ | License: MIT ✓

# Click: Create repository

# Step 2: Clone to your computer

git clone https://github.com/YOUR_USERNAME/agrisage.git

cd agrisage

# Step 3: Create the folder structure

mkdir -p docs backend/api/v1 backend/agents backend/models/db backend/models/schemas

mkdir -p backend/services backend/simulation backend/knowledge backend/ml/vision

mkdir -p backend/data backend/safety backend/tests/unit backend/tests/integration

mkdir -p backend/tests/safety backend/tests/performance backend/tests/golden

mkdir -p mobile/android scripts .github/workflows apps/web-expert

# Step 4: Copy ALL 11 documents into docs/ folder

# (copy the .docx files from wherever you saved them)

# Step 5: Create .gitignore

# (Cline will generate this — see build guide prompt P0.1)

# Step 6: First commit

git add -A

git commit -m 'Initial project structure and all specification documents'

git push origin main

# Step 7: Invite all team members

# GitHub repo page → Settings → Collaborators → Add people

# Add each member's GitHub username

# They get an email invite — they must accept it

## 2.2 All Other Members — Join on Day 1

# ALL OTHER MEMBERS — Do this after Member 1 sends invite

# Step 1: Accept GitHub invite

# Check your email → Click 'Accept invitation'

# Step 2: Clone the repository

# Open terminal (Mac/Linux) or Git Bash (Windows)

git clone https://github.com/MEMBER1_USERNAME/agrisage.git

cd agrisage

# Step 3: Verify you can see the docs/ folder

ls docs/

# Should show all 11 .docx files

# Step 4: Open in VSCode

code .

# This opens the entire project in VSCode

## 2.3 Complete Repository Architecture

This is the full folder structure. Every folder has a purpose.

agrisage/                          ← Root of entire project

│

├── docs/                          ← ALL 11 specification documents

│   ├── 01_PRD.docx

│   ├── 02_TRD.docx

│   ├── 03_AppFlow.docx

│   ├── 04_UIUX_Spec.docx

│   ├── 05_BackendSchema.docx

│   ├── 06_ImplementationPlan.docx

│   ├── 07_Security_Compliance.docx

│   ├── 08_AI_Prompt_Handbook.docx

│   ├── 09_Testing_QA_Playbook.docx

│   ├── 10_Validation_Report.docx

│   └── 11_Master_Build_Guide.docx

│

├── backend/                       ← Python FastAPI server (Member 1 + 2)

│   ├── main.py                    ← FastAPI app entry point

│   ├── config.py                  ← All settings from environment

│   ├── database.py                ← PostgreSQL connection

│   ├── dependencies.py            ← JWT auth dependency

│   │

│   ├── api/v1/                    ← All REST endpoints

│   │   ├── auth.py                ← OTP, login, logout

│   │   ├── farms.py               ← Farm/field/crop CRUD

│   │   ├── observations.py        ← Photo upload

│   │   ├── diagnose.py            ← Advisory generation

│   │   ├── weather.py             ← Weather data

│   │   ├── risk.py                ← Risk scores

│   │   ├── schemes.py             ← Government schemes

│   │   ├── markets.py             ← Market prices

│   │   ├── simulate.py            ← Simulation

│   │   ├── notifications.py       ← Alerts

│   │   └── sync.py                ← Mobile sync

│   │

│   ├── agents/                    ← 14 AI agents (Member 2)

│   │   ├── orchestrator.py        ← LangGraph graph

│   │   ├── intake.py

│   │   ├── vision.py

│   │   ├── weather.py

│   │   ├── crop_stage.py

│   │   ├── knowledge.py

│   │   ├── critic.py

│   │   ├── scheme.py

│   │   ├── soil.py

│   │   ├── decision.py

│   │   ├── explanation.py

│   │   ├── simulation.py

│   │   ├── market.py

│   │   ├── economics.py

│   │   └── monitoring.py

│   │

│   ├── models/                    ← Database and API schemas

│   │   ├── db/                    ← SQLAlchemy ORM models

│   │   └── schemas/               ← Pydantic request/response

│   │

│   ├── services/                  ← Business logic services

│   │   ├── jwt_service.py

│   │   ├── image_security.py

│   │   ├── storage.py             ← Cloudflare R2

│   │   ├── llm_service.py         ← Ollama/Gemini wrapper

│   │   ├── embedding_service.py   ← multilingual-e5-large

│   │   ├── speech_provider.py     ← Bhashini/Android STT

│   │   ├── notifications.py       ← Firebase FCM

│   │   └── morning_briefing.py    ← Daily briefing generator

│   │

│   ├── simulation/                ← Crop simulation

│   │   ├── interface.py           ← Abstract SimulationEngine

│   │   ├── dssat.py               ← DSSAT adapter

│   │   ├── rules.py               ← Offline rule-based

│   │   └── scenarios.py           ← A/B/C scenario builder

│   │

│   ├── knowledge/                 ← RAG knowledge base

│   │   ├── ingestion.py           ← Document pipeline

│   │   ├── retrieval.py           ← Hybrid search

│   │   └── freshness.py           ← Expiry monitoring

│   │

│   ├── ml/vision/                 ← Vision model

│   │   ├── train.py               ← EfficientNet-B3 training

│   │   ├── export.py              ← ONNX export

│   │   └── evaluate.py            ← Metrics and calibration

│   │

│   ├── safety/                    ← Safety checks

│   │   ├── chemical_check.py      ← CIB&RC validation

│   │   └── hallucination_check.py ← LLM output validation

│   │

│   └── data/                      ← Critical JSON data files (Member 4)

│       ├── disease_classes.json   ← 22 ONNX model output classes

│       ├── gdd_thresholds.json    ← Crop stage GDD values

│       ├── stage_disease_map.json ← Stage vulnerability mapping

│       ├── offline_templates_ml.json ← Malayalam offline templates

│       ├── disease_names_ml.json  ← Disease names in Malayalam

│       └── intent_keywords_ml.json   ← Voice intent keywords

│

├── mobile/android/                ← Kotlin Android app (Member 3)

│   └── app/src/main/

│       ├── java/com/agrisage/app/

│       │   ├── ui/

│       │   │   ├── screens/       ← All Compose screens

│       │   │   ├── components/    ← Reusable composables

│       │   │   ├── theme/         ← Colors, typography, shapes

│       │   │   └── navigation/    ← NavGraph

│       │   ├── data/

│       │   │   ├── local/         ← Room entities and DAOs

│       │   │   └── remote/        ← Retrofit API service

│       │   ├── domain/usecases/   ← Business logic

│       │   ├── di/                ← Hilt modules

│       │   └── ml/                ← ONNX inference

│       └── assets/                ← vision_int8.onnx, templates

│

├── alembic/                       ← Database migrations

│   └── versions/                  ← 001 through 017 migration files

│

├── tests/                         ← All tests (Member 5)

│   ├── unit/

│   ├── integration/

│   ├── safety/

│   ├── performance/

│   └── golden/                    ← Labelled disease images

│

├── scripts/                       ← Utility scripts

│   ├── seed_knowledge.py

│   ├── seed_schemes.py

│   ├── evaluate_vision_model.py

│   ├── security_audit.py

│   ├── smoke_tests.py

│   └── deploy.sh

│

├── apps/web-expert/               ← Expert review web dashboard

│

├── .github/workflows/             ← CI/CD pipelines

│   ├── ci.yml

│   └── security.yml

│

├── docker-compose.yml             ← Local development

├── docker-compose.prod.yml        ← Production

├── Dockerfile

├── requirements.txt

├── .env.example

├── .gitignore

├── LICENSE_REGISTRY.md

└── README.md

# SECTION 3: GIT WORKFLOW FOR 5 MEMBERS

## 3.1 Branch Strategy — Simple and Safe

Every member works on their own branch. Never commit directly to main. Team Lead merges everything.

| Branch Name | Owner | What Gets Committed Here |
| --- | --- | --- |
| main | Member 1 merges here | Only tested, working code. Never commit directly. |
| dev/m1-backend | Member 1 | Database, auth, farm CRUD, deployment |
| dev/m2-agents | Member 2 | All AI agents, LangGraph, LLM service |
| dev/m3-android | Member 3 | All Android screens, Room DB, WorkManager |
| dev/m4-data | Member 4 | JSON data files, vision model, knowledge ingestion |
| dev/m5-tests | Member 5 | All test files, CI/CD, security audit scripts |

## 3.2 Daily Git Commands — What Every Member Does

Morning — start of every work day:

# Get latest changes from main

git checkout main

git pull origin main

git checkout dev/YOUR-BRANCH

git merge main

# This keeps your branch up to date with others' merged work

During the day — after completing each task:

# See what you changed

git status

# Stage your changes

git add -A

# Commit with clear message

git commit -m 'M2: implement critic agent conflict detection rules'

# Format: M[your number]: [what you built]

# Examples:

# M1: add JWT auth endpoints with bcrypt OTP hashing

# M3: create camera screen with quality indicator

# M4: create disease_classes.json with all 22 ONNX classes

# M5: add critic safety unit tests

# Push to your branch

git push origin dev/YOUR-BRANCH

When a task is complete and you want it merged to main:

# 1. Push your branch

git push origin dev/YOUR-BRANCH

# 2. Go to GitHub website → Your repo

# 3. You will see a yellow banner: 'dev/YOUR-BRANCH had recent pushes'

# 4. Click: 'Compare & pull request'

# 5. Title: 'M[number]: [what you built]'

# 6. Description: list what files you created/changed

# 7. Click: 'Create pull request'

# 8. Message Member 1 on WhatsApp: 'PR ready for review'

# Member 1 reviews, runs tests, and merges if everything passes

## 3.3 What Member 1 Does to Merge

# Member 1 — reviewing and merging a PR

# 1. Go to GitHub → Pull Requests → click the PR

# 2. Look at 'Files changed' tab — read through the code

# 3. Check: does this match the specification document?

# 4. On your computer:

git checkout main

git pull origin main

git checkout dev/THEIR-BRANCH

git pull origin dev/THEIR-BRANCH

# 5. Run tests

cd agrisage

docker compose up -d

pytest tests/ -v --tb=short

# 6. If tests pass: go back to GitHub PR → 'Merge pull request' → Confirm

# 7. If tests fail: comment on PR with exact error. Do not merge.

## 3.4 Handling Merge Conflicts

A merge conflict happens when two members edit the same file. Here is how to fix it:

# Git will show: CONFLICT (content): Merge conflict in backend/main.py

# Open the conflicted file in VSCode

# You will see markers like this:

<<<<<<< HEAD

your version of the code

=======

their version of the code

>>>>>>> dev/m1-backend

# In VSCode: click 'Accept Current Change' or 'Accept Incoming Change'

# OR manually edit to keep the correct version

# Then:

git add backend/main.py

git commit -m 'Resolve merge conflict in main.py'

⚠ If you are unsure which version to keep in a conflict — do NOT guess. Message the other person on WhatsApp and resolve together. A wrong merge can break the project for everyone.

# SECTION 4: FREE AI TOOL SETUP — EVERY MEMBER

## 4.1 Complete Setup Guide — Day 1 for Every Member

Every member follows ALL these steps on Day 1. Takes about 1.5 hours total.

| Step | Action | Time | Verify It Worked |
| --- | --- | --- | --- |
| 1 | Download VSCode from code.visualstudio.com. Install it. | 10 min | VSCode opens on your computer |
| 2 | In VSCode → Extensions (Ctrl+Shift+X) → Search 'GitHub Copilot' → Install | 5 min | Copilot icon appears in sidebar |
| 3 | In VSCode → Extensions → Search 'Cline' by saoudrizwan → Install | 3 min | Robot icon appears in sidebar |
| 4 | In VSCode → Extensions → Search 'Python' by Microsoft → Install | 3 min | Python extension shows installed |
| 5 | Go to aistudio.google.com → Sign in with Google → Get API key → Copy it | 10 min | You have a long API key starting with 'AIza...' |
| 6 | In VSCode → Click Cline robot icon → Settings gear → API Provider: Google Gemini → Paste API key → Model: gemini-1.5-pro → Save | 5 min | Cline shows 'Connected to Gemini' |
| 7 | In VSCode → Click Copilot icon → Sign in with GitHub free account | 5 min | Copilot chat tab opens |
| 8 | Install Git from git-scm.com. Install with all defaults. | 10 min | Open terminal, type 'git --version', see a version number |
| 9 | Configure Git: git config --global user.name 'YourName' and git config --global user.email 'you@email.com' | 2 min | git config --list shows your name and email |
| 10 | Accept GitHub repo invite from Member 1. Clone repo: git clone [url]. cd agrisage. code . | 15 min | VSCode opens with agrisage folder, docs/ folder visible |
| 11 | Verify Cline works: Click Cline icon → Type 'Hello, list the files in my project' → Cline should respond | 5 min | Cline responds and lists your project files |

## 4.2 How to Use Cline Effectively — For Beginners

Cline is your main coding tool. Here is how to use it step by step:

Step 1: Click the Cline robot icon in the left sidebar of VSCode

Step 2: A chat panel opens on the right side

Step 3: At the top of the chat, type @ to attach documents

Example: @docs/05_BackendSchema.docx

This tells Cline to read that document before answering

Step 4: After the @ mention, paste your prompt from the build guide

Step 5: Press Enter — Cline reads the document and writes code

Step 6: Cline will ask 'Do you want to create this file?' → Click Yes

Step 7: The file appears in your project automatically

Step 8: Review what Cline created — read through it

Step 9: If something looks wrong, use the correction prompt from build guide Part 9

✓ Cline with Gemini 1.5 Pro has a 1 million token context window. This means it can read MULTIPLE documents at once. For complex tasks, attach 2-3 documents. For simple tasks, attach just 1.

⚠ Never blindly run code you have not read. Even if Cline writes it, you must read it. If you do not understand something, ask Cline: 'Explain what this function does in simple terms.'

## 4.3 When You Hit Free Tier Limits

| Tool | Daily Limit | What To Do When Limit Hit |
| --- | --- | --- |
| Gemini API via Cline | 1,500 requests/day free tier | Switch to Claude at claude.ai for that day. Same prompts work. Tomorrow reset continues. |
| GitHub Copilot free | 2,000 completions/month | Use Cline for file generation. Copilot is for inline suggestions only. |
| Claude.ai free | ~30 messages/day | Switch to Gemini via Cline. They alternate well. |
| Google AI Studio direct | Very generous — rarely hit | If hit: wait a few hours, usually resets |

# SECTION 5: MEMBER-BY-MEMBER STEP-BY-STEP GUIDE

## 5.1 MEMBER 1 — Team Lead & Backend — Day-by-Day

You start first. Everyone waits for you to finish Days 1-3 before they can connect to the backend.

| Day | Your Task | Prompt to Use | Verify With |
| --- | --- | --- | --- |
| Day 1 | Create GitHub repo, invite team, create folder structure | Build Guide Part 3 — Prompt P0.1 | ls shows all folders. Team members can clone. |
| Day 2 | Docker + database + requirements.txt | Build Guide Part 3 — Prompt P0.2 | docker compose up -d shows both services running |
| Day 3 | FastAPI app + config + database connection | Build Guide Part 3 — Prompt P0.3 | curl localhost:8000/health returns {status:ok,db_connected:true} |
| Day 4 | All 17 Alembic migrations | Build Guide Part 3 — Prompt P0.4 | docker exec db psql -U agrisage -c '\dt' shows 20 tables |
| Day 5 | Auth endpoints (OTP, JWT, refresh, logout) | Build Guide Part 3 — Prompt P1.1 | POST /auth/send-otp prints OTP in console. POST /auth/verify-otp returns JWT. |
| Day 6 | Farm + field + crop cycle CRUD | Build Guide Part 3 — Prompt P1.2 | POST /farms creates farm. GET /farms returns it. GET /farms/{other_user_id_farm} returns 404. |
| Day 7 | Image upload to Cloudflare R2 | Build Guide Part 3 — Prompt P1.3 | POST /observations with image → image appears in R2 bucket |
| Day 8 | Diagnose endpoint shell (before agents ready) | Build Guide Part 3 — Prompt P1.6 step 3 | POST /diagnose returns 200 with placeholder advisory |
| Days 9-11 | Weather endpoint, risk endpoint, scheme endpoint | Build Guide Part 3 — Prompts P2.x | All 3 endpoints return 200 with correct data shapes |
| Days 12-14 | CI/CD GitHub Actions pipeline | Build Guide Part 3 — Prompt P0.5 | GitHub Actions runs green on push |
| Days 15-22 | Support team, fix backend bugs, review PRs | Daily: check GitHub PRs, merge when tests pass | All team members' code merged to main |

## 5.2 MEMBER 2 — AI Agent Developer — Day-by-Day

You need Member 1's database to be running before Day 6. Days 1-5 you work on agent skeleton and prompts without a running backend.

| Day | Your Task | Prompt to Use | Verify With |
| --- | --- | --- | --- |
| Day 1-2 | Set up your environment, read Doc 8 (AI Prompt Handbook) fully | Setup guide Section 4.1 | VSCode + Cline working |
| Day 3 | LangGraph skeleton + all 14 agent stub files | Build Guide Part 4 — Prompt M2 Task 1 | orchestrator.py exists, all 14 agent files exist |
| Day 4 | Install Ollama on your computer + pull Qwen3-1.7B | ollama pull qwen3:1.7b (free local LLM) | ollama list shows qwen3:1.7b |
| Day 5 | LLM service wrapper with retry + fallback | Build Guide Part 4 — Prompt M2 Task 1 step 3 | llm_service.py exists with retry logic |
| Day 6 | Intake agent + Vision agent (needs Member 4's disease_classes.json) | Build Guide Part 4 — Prompt M2 Task 2 | pytest tests/unit/test_vision.py passes |
| Day 7 | Critic agent — ALL safety rules | Build Guide Part 4 — Prompt M2 Task 2 step 3 | pytest tests/safety/test_critic_safety.py — all 5 tests pass |
| Day 8 | Weather agent with DFI calculation | Build Guide Part 4 — Prompt M2 Task 3 | DFI test cases pass: high humidity→>0.7, dry→<0.3 |
| Day 9 | Crop stage GDD agent | Build Guide Part 4 — Prompt M2 Task 3 step 2 | GDD tests pass: rice at 260 GDD = tillering stage |
| Day 10 | Knowledge RAG agent (needs Member 1's knowledge table) | Build Guide Part 4 — Prompt M2 Task 3 step 3 | Query returns Tier 1 sources for rice blast |
| Day 11 | Decision agent + Explanation agent with correct system prompts | Build Guide Part 4 — Prompt M2 Task 4 | Explanation uses verbatim prompt from Doc 8. Output is valid JSON. |
| Day 12-13 | Connect all agents in LangGraph — test full pipeline | Build Guide Part 4 — Prompt P2.2 | POST /diagnose returns full AdvisoryResponse with all 8 required fields |
| Day 14 | Scheme agent with mandatory eligibility caveat | Build Guide Part 4 — Prompt M2 Task 5 | Scheme output always includes mandatory caveat text |
| Days 15-22 | Monitoring agent, morning briefing, fix agent bugs | Daily fixes as integration issues found | All agents running in pipeline. Advisory in < 8 seconds. |

## 5.3 MEMBER 3 — Android Developer — Day-by-Day

You can start building screens on Day 2 with mock data. You do NOT need the backend running to build the UI.

| Day | Your Task | Prompt to Use | Verify With |
| --- | --- | --- | --- |
| Day 1-2 | Set up environment, read Doc 4 (UI/UX Spec) fully, install Android Studio | Setup guide + Build Guide Part 5 — Prompt M3 Task 1 | Android emulator opens and runs 'Hello World' |
| Day 3 | Android project + all dependencies + Design System (colors, typography, shapes) | Build Guide Part 5 — Prompt M3 Task 1 | AgriSAGETheme compiles. All 30 color tokens defined. |
| Day 4 | All Room database entities + DAOs + Database class | Build Guide Part 5 — Prompt M3 Task 2 | Room compiles without errors. All 9 entities created. |
| Day 5 | Camera screen with quality indicator | Build Guide Part 5 — Prompt M3 Task 3 | Camera opens on emulator. Quality bar turns green/red. |
| Day 6 | Advisory result screen with all composables | Build Guide Part 5 — Prompt M3 Task 4 | Advisory screen shows with ConfidenceBadge, EvidenceCard, ActionCard. |
| Day 7 | Home screen with morning briefing card and action tiles | Build Guide Part 5 — Prompt M3 Task 5 | Home screen shows in Malayalam. 4 tiles visible. |
| Day 8 | Onboarding screens: language selection, phone registration, OTP, farm setup | New Cline prompt: 'Create onboarding flow from App Flow doc Section 1' | Full onboarding flow navigates correctly on emulator |
| Day 9 | Retrofit API service + interceptors + response models | New Cline prompt: 'Create Retrofit service for all endpoints in TRD Section 4.2' | API service compiles. Auth interceptor adds JWT header. |
| Day 10 | Connect home screen to real API (needs Member 1's endpoints) | New Cline prompt: 'Connect HomeViewModel to real backend API' | Home screen loads real farm data from backend |
| Day 11 | Connect camera → diagnose endpoint → advisory screen | New Cline prompt: 'Connect camera capture to POST /diagnose and show result' | Take photo → real advisory appears on screen |
| Day 12 | WorkManager sync for offline | Build Guide Part 5 — Prompt M3 Task 6 | Create farm offline → sync queue shows item → reconnect → item syncs |
| Day 13 | Offline ONNX inference | Build Guide Part 5 — Prompt M3 Task 6 OfflineAdvisoryEngine | Airplane mode → take photo → offline advisory shows in Malayalam |
| Day 14 | Risk dashboard screen, farm timeline screen, scheme screen | New Cline prompts per screen from UI/UX Spec | All 3 screens navigate correctly and display data |
| Day 15 | Push notifications setup (Firebase) | Build Guide Part 5 — Task from Phase 3 | Test notification received on device |
| Days 16-22 | Fix UI bugs, Malayalam review, demo preparation | Daily polish | App looks professional, all text in Malayalam, smooth animations |

## 5.4 MEMBER 4 — Data & Knowledge Engineer — Day-by-Day

Your work on Day 1-3 unblocks everyone else. Member 2 needs your JSON files. The model training runs in background.

| Day | Your Task | Prompt to Use | Verify With |
| --- | --- | --- | --- |
| Day 1-2 | Set up environment, read Doc 10 (Validation Report) Section 5 fully | Setup guide Section 4.1 | VSCode + Cline working, Python installed |
| Day 3 | Create ALL 6 JSON data files from Validation Report Section 5 | Build Guide Part 6 — Prompt M4 Task 1 | All 6 JSON files exist. gdd_thresholds.json has all crops. disease_classes.json has 22 entries. |
| Day 4 | Install PyTorch, torchvision, scikit-learn, pandas | pip install torch torchvision scikit-learn pandas matplotlib | python -c 'import torch; print(torch.__version__)' works |
| Day 5 | Download PlantVillage dataset, organize into training_images/ folder | Search Kaggle for 'PlantVillage dataset' — free download | ls training_images/ shows crop folders with disease subfolders |
| Day 6 | Create vision model training script | Build Guide Part 6 — Prompt M4 Task 2 | train.py runs without error on first 2 epochs |
| Days 7-9 | Train vision model (this takes time — runs in background) | python backend/ml/vision/train.py | After training: training_metrics.json shows macro_f1 > 0.82 |
| Day 10 | Export ONNX model and quantize to INT8 | python backend/ml/vision/export.py | vision_int8.onnx file created. Size < 50MB. |
| Day 11 | Copy vision_int8.onnx to Android assets folder | cp checkpoints/vision_int8.onnx mobile/android/app/src/main/assets/ | File exists in Android assets |
| Day 12 | Knowledge ingestion pipeline + seed_urls.json | Build Guide Part 6 — Prompt M4 Task 3 | ingestion.py runs on first URL. Chunks appear in knowledge_chunks table. |
| Day 13 | Seed 20+ knowledge documents | python scripts/seed_knowledge.py | SELECT COUNT(*) FROM knowledge_chunks shows > 100 rows |
| Day 14 | Seed government schemes database | Build Guide Part 6 — Prompt M4 Task 4 | SELECT * FROM schemes shows PMFBY, PM-KISAN, Kerala schemes |
| Days 15-22 | Collect 100+ field images for golden dataset, label them | Partner with local farmer or use leaf images from Google | tests/golden/ has images with matching .json label files |

## 5.5 MEMBER 5 — QA & DevOps — Day-by-Day

You start writing tests on Day 1 — even before the code exists. Tests define correct behavior.

| Day | Your Task | Prompt to Use | Verify With |
| --- | --- | --- | --- |
| Day 1-2 | Set up environment, read Doc 9 (QA Playbook) fully | Setup guide Section 4.1 | VSCode + Cline working |
| Day 3 | Test infrastructure: conftest.py, fixtures, pytest.ini | Build Guide Part 7 — Prompt M5 Task 1 | pytest tests/ runs (0 tests collected is fine — no errors) |
| Day 4 | ALL unit tests from QA Playbook Sections 2.1, 2.2 | Build Guide Part 7 — Prompt M5 Task 2 | pytest tests/unit/ — tests exist. Some may fail until implementation done. |
| Day 5 | ALL safety tests from QA Playbook Section 2.3 | Build Guide Part 7 — Prompt M5 Task 2 step 3 | tests/safety/test_critic_safety.py exists with 5 test methods |
| Day 6 | ALL integration tests from QA Playbook Sections 3.1, 3.2 | Build Guide Part 7 — Prompt M5 Task 3 | test_auth_api.py and test_rls.py exist |
| Day 7 | GitHub Actions CI/CD pipeline | Build Guide Part 7 — Prompt M5 Task 1 step 5 | Pushing to GitHub triggers CI workflow. See it running in GitHub Actions tab. |
| Day 8 | Run all tests against Member 1's backend | pytest tests/ -v | Report which tests pass and which fail to Member 1 and 2 |
| Days 9-14 | Fix test failures by reporting to relevant member, rerun until all pass | Daily: pytest tests/ -v --tb=short | All unit + safety tests passing. Integration tests passing. |
| Day 15 | Performance test: locust against backend | Build Guide Part 7 — Prompt M5 Task 3 step 3 | locust runs. Report P95 latency to team lead. |
| Day 16 | Security audit script | Build Guide Part 7 — Prompt M5 Task 3 step 4 | scripts/security_audit.py runs 6 checks. All pass. |
| Days 17-20 | End-to-end testing: full farmer journey on real Android device | Manual testing with script from Section 1.3 | Full demo flow works. No crashes. All error states handled. |
| Days 21-22 | Demo preparation: device setup, demo script practice, bug reporting | Manual | Device charged, app installed, demo script memorized |

# SECTION 6: DEMO DAY PREPARATION

## 6.1 What to Prepare Before October 1st

| Item | Who Prepares | Done By |
| --- | --- | --- |
| Android phone with Agri-SAGE installed | Member 3 | September 29 |
| Backend running on Oracle Always-Free server | Member 1 | September 28 |
| Test farm and farmer account created on server | Member 1 | September 30 |
| 20+ disease knowledge documents ingested | Member 4 | September 27 |
| PMFBY and PM-KISAN schemes in database | Member 4 | September 27 |
| Vision ONNX model giving correct diagnoses | Member 4 | September 28 |
| Full demo flow tested end-to-end 3 times | All members | September 30 |
| Backup plan: offline demo if internet fails | Member 3 | September 30 |
| Demo script printed and practiced | All members | September 30 |
| Slide deck (3 slides): what is Agri-SAGE, architecture diagram, demo | Member 1 | September 30 |

## 6.2 The 3-Slide Presentation

Before the live demo, show 3 slides. Keep it under 3 minutes.

- Slide 1: What is Agri-SAGE? — One sentence description. Show the problem (farmer without agronomist). Show the solution (Agri-SAGE). List 3 key features.

- Slide 2: Architecture — Simple diagram showing: Farmer Phone → AI Agents → Knowledge Base + Simulation → Advisory. Show it is offline-capable. Show Malayalam support.

- Slide 3: Progress by October 1st — Checklist of what is working. Roadmap of what comes next. Launch plan.

⚠ Do not show code to HR. Do not show technical architecture details. Show the app working. Show a farmer getting an advisory. That is what matters to HR.

## 6.3 If Something Breaks During Demo

| Problem | Backup Plan |
| --- | --- |
| Internet goes down | Turn on airplane mode — show offline advisory still works. This is actually a feature demonstration. |
| Backend server is down | Use offline mode exclusively. Show all offline features. Explain server will be fixed after demo. |
| Vision model gives wrong result | Show the confidence indicator is low. Explain the system says 'insufficient data' — this is correct behavior, not a bug. |
| Android app crashes | Have a second phone ready with app installed. Or show screenshots of working app. |
| Team member absent | Each member must brief one other member on their part. No single point of failure. |

# SECTION 7: TEAM COMMUNICATION PLAN

## 7.1 Daily Standup — 15 Minutes Every Day

Every day at a fixed time (suggest 9:00 AM), all 5 members answer 3 questions in WhatsApp group:

- 1. What did I complete yesterday?

- 2. What will I do today?

- 3. Is anything blocking me?

If blocked: Tag the specific member who can unblock you. Do not wait silently.

## 7.2 WhatsApp Group Rules

- Group name: Agri-SAGE Team

- Share every commit message in group: 'M2: Critic agent safety checks complete — PR raised'

- Share every blocker immediately — do not wait for standup

- Share test results daily: 'Tests passing: 23/28. Failing: 5 — see PR comment for details'

- No off-topic messages in work hours — keeps focus

- Member 1 has final decision on all merge conflicts and architectural questions

## 7.3 When to Ask for Help

| Situation | Who to Ask |
| --- | --- |
| AI Cline gives wrong code | First: try correction prompt from Build Guide Part 9. If still wrong: ask team in WhatsApp. |
| Test is failing and you don't know why | Post exact error message in WhatsApp. Tag Member 5 (QA). |
| Backend endpoint not working | Tag Member 1 in WhatsApp with exact error and curl command used. |
| Android screen not looking right | Tag Member 3. Share screenshot. |
| Confused about specification document | Tag Team Lead. They will find the right section. |
| Git conflict you can't resolve | STOP. Tag Member 1 immediately. Do not force-merge. |
| Free AI limit reached | Announce in WhatsApp: 'M3 hit Gemini limit for today — switching to Claude'. Others know your progress. |

AGRI-SAGE TEAM SPRINT PLAN v1.0

October 1st Demo · 22 Days · 5 Members · All Free Tools · Work Parallel

One task per session · Commit daily · Communicate blockers immediately · Verify before merging